## Sheet1
| Week 1 (25 Feb - 2 Mar) | Week 2 (3 Mar - 9 Mar) | Week 3 (10 Mar - 16 Mar)
1 | Product review and requirements | Library Design | PCB Design
2 | Components Selection & short listing | Library Design / Schematic Design | PCB Design
3 | Components Selection & short listing LCSC Components | Schematic Design | PCB Design
4 | Components Selection & short listing LCSC Components | Schematic Design | PCB Design
5 | Component finalization | Schematic Design | PCB Design / Mechanical Enclosure Design
6 | Library Design | Schematic Review | PCB Design Review
| Week 4 (17 Mar - 23 Mar) | Week 5 (24 Mar - 30 Mar) | Week 6 (31 Mar - 6 Apr)
1 | Order Placement for PCB/PCBA on JLCPCB | Reserved for mechanical design to be decided once on PCB design | Expected Arrival of PCB from China
2 | Reserved for mechanical design to be decided once on PCB design |  | Hardware Testing
3 |  |  | Make changes to schematic - If any
4 |  |  | Reorder if required
5 |  |  | Electrical Design Ready For Production
6